## Page_1
Singapore Changi SIN T2
Form No.
[5 empty] | ATR Installation Inspection Report | [13 empty] | Revision No. |  | 01
[19 empty] | Page No |  | 1/1
Location |  | Area : ACB30 | [10 empty] | Gridline: |  |  |  | Floor No/ Level
Date
Drawing No : | [12 empty] | Rev. No :
System : | [12 empty] | Subsystem :
| Frame complete | Frame securely fastened to the platform or floor | Datalogic cables and devices labeled | Datalogic cables connected EBC Bus | Datalogic cables connected SyncNet Bus | Datalogic cables connected Hybrid Network | Datalogic cables Connected Power bus | Datalogic cables are nicely fixed and grouped inside the cable ducts | P100 ProfiNET communication cable connected Primary SC5000 | P100 ProfiNET communication cable connected Secondary SC5000 | Encoder cable connected to primary controller (SC5000) | Encoder cable connected to secondary controller (SC5000) | Ethernet cables from Beumer (Image net: VCS / P2) connected to Eth. Ports | 230 Vac Power line and Earth connected to PWR-480B M | 230 Vac Power line and Earth connected to PWR-480B S | All hardware fixed to the frame | PWR-480B Primary - Is securely fastened | PWR-480B Primary lock is functioning | PWR-480B Secondary - Is securely fastened | PWR-480B Secondary lock is functioning | It is necessary to measure the resistance between two outer positions | on the bolts of the frame to check for low resistance. | This is needed for good electrical ground conduction. | Measure this on three different positions. | The Ohm-meter should not read higher than 1Ω
ACB300.ATR040
Inspected by | [7 empty] | Name and Signature | [9 empty] | Date
Witnessed by | [7 empty] | Name and Signature | [9 empty] | Date
[8 empty] | Name and Signature | [9 empty] | Date